Multi-Agent RAG System - 4-Week Sprint Plan

Project Scope

Implementing Section 1: Multi-Collection RAG with Category-Specific Processing and Section 2: Multi-Agent Architecture with 6 team members across 3 workstreams.

Team Structure & Workstream Allocation

🔵 Workstream 1: Data Platform & Retrieval Engine

Team Members: 2 people
Focus: Database, document processing, vector search, and retrieval infrastructure

🟢 Workstream 2: Agent Framework & Orchestration

Team Members: 2 people
Focus: Agent architecture, LLM integration, orchestration logic

🟡 Workstream 3: Integration & User Interface

Team Members: 2 people
Focus: API layer, UI, end-to-end integration, testing

📅 4-Week Sprint Breakdown

🔵 WORKSTREAM 1: Data Platform & Retrieval Engine

Week 1: Foundation & Schema Setup

Sprint 1.1: Database Architecture (Days 1-2)

Owner: Dev 1

- [ ] Set up PostgreSQL with pgvector extension

- [ ] Create database schema for all tables (documents, chunks, categories, projects)

- [ ] Implement database migration scripts (Alembic)

- [ ] Create indexes (vector, full-text, metadata)

- [ ] Set up connection pooling

- [ ] Write database utility functions

Deliverable: Fully functional database with schema, ready for data ingestion

Sprint 1.2: Category Management System (Days 3-4)

Owner: Dev 2

- [ ] Create categories table seed data (Requirements, Business Rules, Design, Tech Specs, Contracts, Proposals)

- [ ] Build category configuration system (chunking strategies, metadata schemas)

- [ ] Implement category CRUD operations

- [ ] Create category-specific metadata validators

- [ ] Build project management functions (create, list, delete projects)

Deliverable: Category management system with predefined configurations

Sprint 1.3: Document Processing Pipeline (Days 5-7)

Owner: Dev 1 & Dev 2 (pair programming)

- [ ] Implement document loaders (PDF, DOCX, TXT, MD)

- [ ] Build category-specific chunking strategies

  - Requirements: semantic chunking with REQ-ID detection

  - Business Rules: rule-based splitting (if-then patterns)

  - Design Docs: hierarchical chunking

  - Tech Specs: preserve code blocks and API endpoints

  - Contracts: clause-based chunking

  - Proposals: section-based chunking

- [ ] Create metadata extraction for each category

- [ ] Implement embedding generation (OpenAI text-embedding-3-small)

- [ ] Build document processing orchestrator

Deliverable: Complete document processing pipeline that handles all 6 categories

Week 2: Advanced Retrieval System

Sprint 1.4: Vector Search Implementation (Days 8-10)

Owner: Dev 1

- [ ] Implement category-aware vector similarity search

- [ ] Build hybrid search (vector + keyword using PostgreSQL full-text search)

- [ ] Create metadata filtering layer (filter by category, project, tags, dates)

- [ ] Optimize vector index parameters (tune HNSW/IVFFlat)

- [ ] Implement batch embedding operations

- [ ] Add query result caching

Deliverable: High-performance retrieval engine with hybrid search

Sprint 1.5: Multi-Stage Retrieval Pipeline (Days 11-14)

Owner: Dev 2

- [ ] Build CategoryAwareRetriever class

- [ ] Implement parallel retrieval across multiple categories

- [ ] Create cross-category fusion and reranking logic

- [ ] Build traceability system (chunk relationships, document relationships)

- [ ] Implement related chunks retrieval (for requirements → design links)

- [ ] Create retrieval performance monitoring

- [ ] Add retrieval quality metrics (precision@k, MRR)

Deliverable: Advanced retrieval system with traceability and reranking

Week 3: Optimization & Analytics

Sprint 1.6: Performance Optimization (Days 15-17)

Owner: Dev 1

- [ ] Benchmark and optimize database queries (EXPLAIN ANALYZE)

- [ ] Implement query result pagination

- [ ] Add database-level caching for frequent queries

- [ ] Optimize embedding batch processing

- [ ] Create materialized views for analytics

- [ ] Implement database backup/restore scripts

Deliverable: Optimized data platform with 2x faster retrieval

Sprint 1.7: Analytics & Monitoring (Days 18-21)

Owner: Dev 2

- [ ] Build query logging system (log all queries with performance metrics)

- [ ] Create analytics queries (category usage, query patterns, retrieval quality)

- [ ] Implement traceability matrix generation

- [ ] Build gap analysis function (requirements without design)

- [ ] Create impact analysis function (change impact across documents)

- [ ] Build document recommendation system

Deliverable: Analytics dashboard backend and monitoring system

Week 4: Testing & Documentation

Sprint 1.8: Integration Testing & Polish (Days 22-28)

Owner: Dev 1 & Dev 2

- [ ] Create test dataset with sample documents (each category)

- [ ] Write unit tests for all retrieval functions

- [ ] Test category-specific chunking strategies

- [ ] Benchmark retrieval performance (speed, accuracy)

- [ ] Document database schema with ER diagram

- [ ] Write API documentation for retrieval functions

- [ ] Create data platform user guide

Deliverable: Fully tested and documented data platform

🟢 WORKSTREAM 2: Agent Framework & Orchestration

Week 1: Agent Foundation

Sprint 2.1: Base Agent Architecture (Days 1-3)

Owner: Dev 3

- [ ] Design BaseAgent abstract class

- [ ] Implement AgentContext and AgentResponse data structures

- [ ] Build LLM integration layer (OpenAI API wrapper)

- [ ] Create prompt building utilities

- [ ] Implement response parsing and citation extraction

- [ ] Add error handling and retry logic

- [ ] Build agent configuration system

Deliverable: Base agent framework ready for specialization

Sprint 2.2: Specialized Agent Implementation (Days 4-7)

Owner: Dev 3 & Dev 4 (divide agents between them)

Dev 3 responsibilities:

- [ ] Implement RequirementsAgent

  - Custom system prompt for requirements analysis

  - can_handle_query() logic with requirement keywords

  - Gap detection function

  - Requirement traceability

- [ ] Implement BusinessRulesAgent

  - System prompt for rule logic

  - Rule conflict detection

  - Condition-action extraction

- [ ] Implement DesignAgent

  - Architecture analysis prompts

  - Component traceability

  - Design pattern detection

Dev 4 responsibilities:

- [ ] Implement TechSpecsAgent

  - API documentation specialist

  - Code example extraction

  - Technical constraint analysis

- [ ] Implement ContractsAgent

  - Legal terms analysis (with disclaimers)

  - Obligation tracking

  - Contract comparison

- [ ] Implement ProposalsAgent

  - Scope and estimate analysis

  - Cost breakdown

  - Timeline extraction

Deliverable: 6 fully functional specialized agents

Week 2: Orchestration Logic

Sprint 2.3: Orchestrator Core (Days 8-11)

Owner: Dev 3

- [ ] Build OrchestratorAgent class

- [ ] Implement query analysis using LLM (intent detection, complexity assessment)

- [ ] Create agent selection algorithm (relevance scoring)

- [ ] Build agent execution workflows:

  - Parallel execution (independent queries)

  - Sequential execution (dependent queries)

  - Hybrid execution (staged queries)

- [ ] Implement conversation state management

- [ ] Add query metadata tracking

Deliverable: Core orchestration engine

Sprint 2.4: Response Synthesis & Conflict Resolution (Days 12-14)

Owner: Dev 4

- [ ] Build multi-agent response synthesis

- [ ] Implement conflict detection between agent responses

- [ ] Create consensus-building logic

- [ ] Build follow-up agent suggestions

- [ ] Implement confidence score aggregation

- [ ] Add citation merging and deduplication

- [ ] Create response quality assessment

Deliverable: Intelligent response synthesis system

Week 3: Advanced Agent Features

Sprint 2.5: Agent Collaboration (Days 15-18)

Owner: Dev 3

- [ ] Implement agent-to-agent communication protocol

- [ ] Build cross-agent context sharing

- [ ] Create traceability chains (Requirements → Design → Tech Specs)

- [ ] Implement agent memory (remember previous interactions)

- [ ] Add agent performance tracking

- [ ] Build agent recommendation system (agents suggest other agents)

Deliverable: Collaborative multi-agent system

Sprint 2.6: Prompt Engineering & Optimization (Days 19-21)

Owner: Dev 4

- [ ] Optimize system prompts for each agent (A/B testing)

- [ ] Implement few-shot examples for better responses

- [ ] Create prompt versioning system

- [ ] Add dynamic prompt adjustment based on query complexity

- [ ] Implement token usage optimization

- [ ] Build prompt performance analytics

Deliverable: Optimized prompts with measurable quality improvement

Week 4: Testing & Integration

Sprint 2.7: Agent Testing & Quality Assurance (Days 22-25)

Owner: Dev 3 & Dev 4

- [ ] Create test queries for each agent (functional, edge cases)

- [ ] Test orchestrator decision-making (agent selection accuracy)

- [ ] Validate response synthesis quality

- [ ] Test multi-agent collaboration scenarios

- [ ] Benchmark LLM API costs and latency

- [ ] Test error handling and fallback mechanisms

Deliverable: Fully tested agent system

Sprint 2.8: Documentation & Handoff (Days 26-28)

Owner: Dev 3 & Dev 4

- [ ] Document agent system architecture

- [ ] Write agent development guide (how to add new agents)

- [ ] Create prompt engineering guidelines

- [ ] Document orchestration logic

- [ ] Write API documentation for agent functions

- [ ] Create troubleshooting guide

Deliverable: Complete agent framework documentation

🟡 WORKSTREAM 3: Integration & User Interface

Week 1: API Layer

Sprint 3.1: Backend API Foundation (Days 1-3)

Owner: Dev 5

- [ ] Set up FastAPI/Flask application structure

- [ ] Design RESTful API endpoints:

  - POST /api/documents/upload - Upload and process documents

  - GET /api/documents - List documents by project/category

  - DELETE /api/documents/{id} - Delete document

  - POST /api/query - Ask questions (main query endpoint)

  - GET /api/projects - List projects

  - GET /api/categories - List categories

  - GET /api/analytics - Get system statistics

- [ ] Implement request/response models (Pydantic)

- [ ] Add authentication middleware (if needed)

- [ ] Set up CORS for frontend

Deliverable: RESTful API structure ready for integration

Sprint 3.2: API Integration with Workstreams 1 & 2 (Days 4-7)

Owner: Dev 5 & Dev 6

- [ ] Integrate data platform (Workstream 1) with API endpoints

  - Connect document upload to processing pipeline

  - Wire retrieval functions to query endpoint

  - Connect analytics functions to API

- [ ] Integrate agent system (Workstream 2) with API

  - Wire orchestrator to query endpoint

  - Handle conversation state via sessions

  - Stream agent responses to frontend

- [ ] Implement file upload handling (multipart/form-data)

- [ ] Add response streaming (SSE or WebSocket) for real-time updates

- [ ] Implement error handling and validation

Deliverable: Fully integrated backend API

Week 2: User Interface

Sprint 3.3: UI Foundation (Days 8-10)

Owner: Dev 6

- [ ] Set up Streamlit application structure

- [ ] Design page layout (sidebar + main area + analytics panel)

- [ ] Build project selector component

- [ ] Create category filter checkboxes

- [ ] Implement document upload interface with drag-and-drop

- [ ] Build chat interface for conversations

- [ ] Add session state management

Deliverable: UI skeleton with basic components

Sprint 3.4: Chat & Query Interface (Days 11-14)

Owner: Dev 6

- [ ] Build conversational chat UI

- [ ] Display user and assistant messages

- [ ] Show typing indicators during query processing

- [ ] Display agent activity (which agents are working)

- [ ] Show confidence scores and agent agreement indicators

- [ ] Implement citation display with source links

- [ ] Add expandable source panels

- [ ] Show traceability information (requirement → design links)

Deliverable: Functional chat interface with rich response display

Week 3: Advanced UI Features

Sprint 3.5: Document Management Interface (Days 15-17)

Owner: Dev 5

- [ ] Build document list view (with filters by category, project, date)

- [ ] Add document preview functionality

- [ ] Implement document delete with confirmation

- [ ] Show document processing status (processing, indexed, failed)

- [ ] Display document metadata (version, author, tags)

- [ ] Add bulk document upload

- [ ] Create document relationship visualization

Deliverable: Complete document management interface

Sprint 3.6: Analytics Dashboard (Days 18-21)

Owner: Dev 6

- [ ] Build analytics dashboard with key metrics:

  - Total documents, chunks, queries

  - Average response time and confidence

  - User satisfaction scores

- [ ] Create category usage charts (bar/pie charts)

- [ ] Display agent usage statistics

- [ ] Show traceability matrix visualization

- [ ] Implement gap analysis display (requirements without design)

- [ ] Add query history view

- [ ] Create performance monitoring charts

Deliverable: Interactive analytics dashboard

Week 4: End-to-End Integration & Testing

Sprint 3.7: System Integration Testing (Days 22-25)

Owner: Dev 5 & Dev 6

- [ ] Test complete user workflows:

  - Upload document → Process → Query → Get answer with citations

  - Multi-category queries

  - Traceability queries (REQ → Design)

  - Gap analysis

- [ ] Test error scenarios (bad uploads, failed processing, LLM errors)

- [ ] Performance testing (concurrent users, large documents)

- [ ] UI/UX testing (responsiveness, loading states, error messages)

- [ ] Cross-browser testing

- [ ] Mobile responsiveness testing

Deliverable: Fully integrated and tested system

Sprint 3.8: Demo Preparation & Documentation (Days 26-28)

Owner: Dev 5 & Dev 6

- [ ] Create demo dataset (sample documents for all 6 categories)

- [ ] Prepare demo script with impressive queries

- [ ] Record demo video (5-7 minutes)

- [ ] Write user guide with screenshots

- [ ] Create README with:

  - Project overview

  - Architecture diagram

  - Setup instructions

  - Usage examples

  - API documentation

- [ ] Prepare presentation slides

- [ ] Document known issues and future enhancements

Deliverable: Production-ready application with complete documentation

🔄 Cross-Workstream Integration Points

Integration Checkpoint 1 (End of Week 1)

All Teams Meet

- Workstream 1 demos document processing

- Workstream 2 demos base agent functionality

- Workstream 3 demos API structure

- Goal: Ensure interfaces are aligned (data models, API contracts)

Integration Checkpoint 2 (End of Week 2)

All Teams Meet

- Workstream 1 demos retrieval engine with sample queries

- Workstream 2 demos orchestrator with agent selection

- Workstream 3 demos API integration with mock data

- Goal: Test data flow between systems

Integration Checkpoint 3 (End of Week 3)

All Teams Meet

- Workstream 1 demos analytics and traceability

- Workstream 2 demos multi-agent collaboration

- Workstream 3 demos full UI with live backend

- Goal: End-to-end testing begins

Final Integration (Week 4, Days 22-24)

All Teams Collaborate

- Merge all components

- Resolve integration issues

- Final testing and polish

- Goal: Production-ready system

📊 Success Metrics (Measured at End of Week 4)

Data Platform (Workstream 1)

- [ ] 6 category-specific processors working

- [ ] Retrieval accuracy: Precision@5 > 80%

- [ ] Query latency: < 500ms average

- [ ] Successfully processes 100+ test documents

Agent System (Workstream 2)

- [ ] 6 specialized agents operational

- [ ] Orchestrator selects correct agents 90%+ of time

- [ ] Multi-agent synthesis produces coherent answers

- [ ] LLM API cost: < $0.10 per query

Integration & UI (Workstream 3)

- [ ] All API endpoints functional

- [ ] UI handles all user workflows

- [ ] Zero critical bugs

- [ ] Demo-ready with polished UX

🎯 Daily Standups (15 minutes)

Format:

- What did you complete yesterday?

- What will you work on today?

- Any blockers?

Slack/Discord channel: Keep async updates here for visibility

🚀 Sprint Rituals

Weekly Sprint Planning (Monday, 1 hour)

- Review last week's deliverables

- Plan current week's tasks

- Identify dependencies and risks

Mid-Week Sync (Wednesday, 30 minutes)

- Progress check-in

- Resolve blockers

- Adjust priorities if needed

Weekly Demo (Friday, 1 hour)

- Each workstream demos progress

- Collect feedback

- Celebrate wins

🛠️ Technical Stack Summary

Workstream 1:

- PostgreSQL + pgvector

- Python (psycopg2, SQLAlchemy)

- LangChain (for chunking utilities)

- OpenAI API (embeddings)

Workstream 2:

- Python

- OpenAI API (GPT-4o-mini)

- LangChain (optional, for agent helpers)

Workstream 3:

- FastAPI (backend)

- Streamlit (frontend)

- Python requests (API integration)

📦 Deliverable Checklist (End of Week 4)

- [ ] Functional multi-agent RAG system

- [ ] 6 category-specific document processors

- [ ] 6 specialized AI agents with orchestrator

- [ ] Web-based chat interface

- [ ] Document management system

- [ ] Analytics dashboard

- [ ] Complete documentation (README, API docs, user guide)

- [ ] Demo video

- [ ] Test dataset with sample queries

- [ ] GitHub repository with clean code

This plan ensures:

- Parallel work - All 3 workstreams can work independently

- Clear ownership - Each team knows their deliverables

- Integration points - Regular syncs prevent integration hell

- Achievable scope - 4 weeks with 6 people on focused tasks

- Production-ready output - Complete system with documentation

Ready to sprint? Let's build this! 🚀